## Burn Down Chart
Project Title: Milestone 1 Release #: 1 Sprint #: 1
| User Story ID | User Story | Tasks | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| 1 | UML Diagrams | Create use case, component, class, and deployment diagram | John Harrison | 8 | 2 | 0 | 2 | 0 | 2 | 0 | 2
| 2 | Reseach and Identify IoT Applications | Find IoT idea to program and propose | John Harrison and Zach Swoveland | 8 | 2 | 2 | 0 | 2 | 2 | 0 | 0
| 3 |  | Task 3 | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 |  | Task 4 | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 |  | Task 5 | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 |  | Task 6 | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 |  | Task 7 | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 |  | Task 8 | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 |  | Task 9 | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 |  | Task 10 | Team Member | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 16 | 12 | 10 | 8 | 6 | 2 | 2 | 0

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints).
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log.
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C.
Step 4 | Break the User Story into a series of step by step development tasks in Column D.
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories.
Step 6 | Assign the User Story to a single team member in Column E.
Step 7 | Repeat Steps 4-6 for each User Story that has been planned for this Sprint.
Step 8 | At the end of each day, each team member should update the effort hours that were worked on their User Story to burn their work down.
Step 9 | After each Daily Standup, each team member should review the Burn Down Chart to ensure your Sprint will be delivered on time.